## Cat A
Category A: Shoreline/Streambank Issues
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
A1 | Restore severe and moderate streambank erosion sites identified in CRA inventory. Use whole-tree revetments where practicable to improve aquatic habaitat while stabilizing streambanks. | H | $120 per linear foot | 300000 |  |  |  | CRA | G.L. Fisheries Trust; Grants | 2; 3c; 3e
A2 | Update streambank inventory on Little Manistee River and major tributaries on 10-year cycle. | M |  | 14000 | X | inventory updated | X | CRA | Trout Unlimited; G.L. Fisheries Trust | 3c; 3e
A3 | Work with conservation districts and MSU extension to demonstrate natural shoreline protection techniques on Cool, Syers and other developed lakes in the Watershed. | M | $5,000 per site | 15000 |  |  |  |  | Private Property owners; MSUE; Cons. Dists | 3c
A4 | Complete removal of sand-berm dam at Syers Lake to restore natural lake configuration and perenneal flow to Syers Creek | H | 120000 | 120000 | Project complete | Creek monitored | C | LMWCC; CRA; private landowners | LMWCC; T.U.; Grants; Private landowner funds | 2e | Funding committed for 2018/2019
A5
A6

## Cat B
Category B: Stormwater and Run-off
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
B1 | Update stormwater infrastructure and impervious surface maps. Identify problem sites and institute Green Infrastructure BMP's for all new construction. | L | [7 empty] | 2d; 3c
B2 | Inventory & monitor all streams for nutrients, E. coli, and other pollutants. Institute BMP's as appropriate. | H | $1,000 year | 10000 | Existng program continues | Progbram expanded to additional sites | C | LMWCC | LMWCC funds; volunteers | 3a; 3b; 3e | This is a continuation and expansion of existing LMWCC program
B3 | Promote shoreline stewardship education through Michigan Natural Shoreline Partnership | M | [7 empty] | 3c; 3e
B4 | Promote reforestation of areas within the stream corridor to reduce storm runoff and thermal pollution. | H | $5,000 per year | 50000 | Sites identified | Reforstation activity on 5 sites | Reforestation activity on 10 sites | Provate Land owners; Conservation Districts; U.S. Forest Service; MDNR | Private funds; grants | 2a; 2c; 2d
B5 | Encourage voluntary private land stewardship practices such as native plantings, rain gardens, conservation easements, and preservation of wildlife habitat. | H | $2,000 per rain garden | 24000 | 2 rain gardens installed | 5 rain gardens installed | 12 (total) rain gardens installed | Private funds | MSUE; Conservation Dists. | Goal 2; 3a

## Cat C
Category C: Planning, Zoning and Land Use
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
C1 | Work with township and county planners to develop cooperative land-use practices that extend across government boundaries to protect the entire watershed. | H | $3,000 per township | 25000 | Create multi-jurisductional task force | Fundng secured | Program in place | Townships; MSUE; LMWCC; AES | Will require outside grant asistance. Tribal 2 pct. Funding | Goal 1; Goal 5 | See task L7. This task must be coordinated with I/E component
C2 | Identify locally important viewsheds, incorporate protection into master plans and local zoning ordinances to maintain the natural and rustic character of the watershed. | M | Included in C1 |  |  | Sites identified for protection |  |  |  | Goal 4
C3 | Develop and adopt ordinances to prevent introduction of terrestrial and aquatic invasive species, and permit treatment of existing infestations | M | No new costs identified |  | Provide model ordinances to townships | C | C | MTA; ISN; township govts |  | 1d; 3f | Model ordinances available through ISN's. May require state legislation
C4 | Investigate the possibility of a multi-jurisdictional zoning overlay district to establish uniform, locally based rules for development within the Little Manistee Watershed and River Corridor. | H | See C1 | [6 empty] | Goal 1; Goal 5 | This is a specific task included in the more general actiivities of C1
C5 | Promote 'green infrastructure' principles including cluster development for rural residential, and low impact stormwater design requirements as part of local planning and zoning process for new developments. | L | No costs identified | [6 empty] | 5a
C6 | Begin public education regarding the pros and cons of Michigan Natural River designation; promote such designation if local support exists. | H | Variable | [6 empty] | 1f | This requires coorodination with I/E program as well as local planners

## Cat D
Category D: Road-Stream Issues
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
D1 | Update existing stream crossing inventory every 10 years to reflect changes & document improvements | H | 12000 | 12000 | X | New Inventory Complete | C | CRA; LMWCC | Tribal 2 pct. Funding; Great laskes Fisheries Trust | 2e; 3e
D2 | Restore and protect road-stream crossings identified in the inventory as sites of severe or moderate concern, using appropriate BMP's. Restore and protect additional sites on road-stream crossing inventory as conditions require and funding becomes available. | H |  |  | 2 sites addressed | 5 sites addressed | all severs sites improved | CRA; LMWCC | Grant funding required; Road commissions; MDOT | 2e; 3e | Cost estimates based on existing inventory -- likely to increase as new needs identified
D3 | Identify sites where private roads may have an impact on surface water qualiity. Work with property owners to minimize movement of sediments, nutrients, salts, etc. into adjacent water | M | varies |  |  | Sites Identified | C | Private land owners; CRA | Private funds | 3e
D4 | Develop & institute policies regarding use of dust control agents on unpaved roads near surface waters. Institute BMPs to prevent dust-control agents from entering surface waters. | L | unknown |  |  | Policies developed |  | Road Commissions; MDOT; MDEQ |  | 3e

## Cat E
Category E: Land Protection and Management
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
E1 | Work with Land Conservancies and/ or other agencies to develop a systematic priority parcel analysis for significant lands in Mason County and Lake County segments of the Watershed. Update the existing analysis for the Manistee County segment. | M |  | 10000 | Manistee analysis cmplete | Analysis complete for Lake and Mason | C | GTRLC; Land Conservancies | Grants; private donations | 4b; 4f; Goal 5
E2 | Assist and support state and/or local government acquisition of property for protection of water quality, threatened or endangered species, wildlife habitat and other sensitive ecological features | M |  | 500000 |  | 2 sites protected | C | MDNR; USFS; townships; Land conservancies | Nat. Res. Trust Fund. USFS funds | Goal 5
E3 | Support land-protection and land purchase activities on high-priority sites throughout watershed, including conservation easements and transfer/purchase of development rights where appropriate. | H |  | 500000 |  | 2 sites protected | C | Land Conservancies; private land owners | Nat. res. Trust Funds; Private donations | Goal 5
E4 | Promote participation in NRCS programs and Michigan Agriculture Environmental Assurance Program (MAEAP) to encourage BMP's in agricultural operations | L |  | No costs identified | X | 1 farm certified | C | Farm owners; MDARD |  | 3e

## Cat F
Category F: Habitat for Fish and Wildlife
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
F1 | Maintain multiple-use management policies on public lands. Preserve upland habitat and wildlife corridors. Discourage new roads in state forest and wetland areas | H |  | No new costs | [5 empty] | 4a; 4b; 4c | This is a continuation of current policies
F2 | Conduct fishery surveys on the Little Manistee River on a minimum 10 year cycle to monitor changes & evaluate stocking & managment programs. | H |  | 30000 |  | New survey complete | C | MDNR; Trout unlimited; LRBOI | MDNR funds | 4a; 4e
F3 | Maintain current fish stocking & management strategies unless changes are warranted by scientific studies such as in F2 | M |  | No New costs | C | C | C | MDNR; Trout unlimited; LRBOI |  | 4a | Continuation of current policies
F4 | Install and maintain fish habitat improvement structures as appropriate. Consider instream habitat and fish passage implications of all road crossing and bank stabilization projects. | M | $5,000 per site | 120000 | Woody debris installed, per plan | C | C | LMWCC; MDNR; CRA; Trout unlimited | Private donations; volunteer in-kind | Goal 2 | Funds committed for woody debris work in 2018/2019
F5 | Evaluate & document stream and streamside habitat, including shade and forest cover for the Little Manistee River and major tributaries. | M | [7 empty] | Goal 2 | This can be included in an enhanced bank erosion survey
F6 | Restudy & document habitat and fishery potential in each of small lakes and streams in watershed, many of which have not been evaluated in more than 50 yrs. | L |  | 50000 |  | Inventory complete |  | MDNR; private land owners | Grants; MDNR funds | 4a
F7 | Evaluate fishery potential in the Luther Millpond and sites upstream of the Luther Dam. | H | 30000 | 30000 | Develop plans for cooperative study with MDNR; Village and Township | Complete Study | Publicize study's results and recommendation | Village of Luther; Ellsworth Twp. Trout Unlimited; MDNR; LMWCC | Grants; LRBOI 2 pct. Funds | 1a; 1f
F8 | Closely monitor operation of Luther Dam and spillway. Recommend changes as appropriate. Specify which agency (Village or MDNR) is responsible for operation of the dam. | H | No new costs identified |  | Develop operation and monitoring plan | C | C | Village of Luther; Ellsworth Twp. MDNR; LMWCC | Village and township funds | 2b; 2e | This item could be a short-term option, depending on action in F9
F9 | Develop long-term options for removal of the Luther Dam and restoration of the Millpond area and upstream tributaries. Recognize that the dam is the property of the village, and removal/restoration can occur only if village residents and officials determine it is in their best interests. | M |  | Variable: $50,000 to $2 million | Phase 1; create working group; identify long term costs and benefits of maintaining the dam/millpond | Phase 2: identify benefits and costs of fish passage systems; stream restoration; dam removal or other operational changes | Phase 3: Act on appropriate phase 2 findings | Village of Luther; Ellsworth Twp. LMWCC; MDNR; MDEQ | State of federal grants required | 1a; 2b; 2e | Changes in dam operation and/or fish passage may have modest costs; Complete removal and stream restoration; would cost up to $2 million

## Cat G
Category G: Recreation, Safety, Navigation and Human Health
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
G1 | Continue and expand volunteer monitoring for E. coli and other pothential pathogens | H | $2,000 per year | 20000 | Monitoring in placec | C | C | LMWCC, lake associations |  | 3a; 3b
G2 | Work with State Forest and National Forest staff and ORV groups to ensure that motorized trails are designed and used in ways that do not negatively impact water quality. | H | No new costs identified |  | Trails inspected and site issues identifieid | Sites corrected | C | MDNR; USFS; Snowmobile and ORV organizations | Trail program funds | 4b; 4c; 4e
G3 | Initiate "adopt a stream" or similar volunteer program for ongoing river clean-up and tree management. | M | No new costs identified |  | Program in place | C | C | Conservation Districts; |  | 1c; 1e
G4 | Monitor paddlecraft volume to ensure that such use does not exceed the river's carrying capacity. | L | No new costs identified |  | Monitoring dates/criteria identified | Program in place | C | LMRCC; Private Landowners |  | 4b; 4d; 4e

## Cat H
Category H: Hydrology, Groundwater and Wetlands
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
H1 | Install and monitor permanent gauges throughout watershed to evaluate & report stream flow, water temperature, and high-low water conditions. Investigate emerging technologies for automatic sensors, if USGS gauging is not available. | H | variable | $5,000 - $35,000 | Permanent gauges in place |  |  | LMWCC; Conservation Districts; USFS; USGS; MDNR | USGS; Local donors | 2a | $35,000 is estimate for USGS gauging station
H2 | Actively support the portion of the Michigan Water Strategy that calls for a statewide system of groundwater and surface water monitoring. Coordinate letter of support campaign with watersheds in region. | M | No New Costs identified |  | Develop and distribute letter of support; coordinate communications | C | C | LMWCC; Michigan Legislature |  | 2a; 2d; 5c; 5e
H3 | Work with local government to enact ordinances that regulate installation of new impervious surfaces and mandate BMP's to control stormwater and mitigate impact of new and existing impervious surfaces. | M |  | No new costs |  |  |  | Twp planning comms. | Grants, in-kind labor | 1a; 1f; 2d; 3c; 4e | This element of groundwater protection is also included in categories B and C, and in education component (Cat L)
H4 | Protect wetland areas from development; initiate programs to educate the public about the role of wetlands in water quality | M |  | 5000 |  | Wetland program offered to schools and service groups | C | MDEQ; MDNR, Twp. Planning comms.; LMWCC | Conservation Districts; Inland Lake Groups; townships | 1a;2a; 2d | Wetland education costs also included in I/E progam estimates (Category L)
H5 | Adopt state and local rules, protective of groundwater, to monitor and regulate the practices of horizontal drilling & hydraulic fracturing for oil & gas extraction, including associated infrastructure and disposal facilities | H |  | unknown | C | C | C | Legislature, MDEQ, Twp planning comms. |  | 2a; 2d; 4f
H6 | Monitor for nitrates in well water, especially at sites with light soils and historic agricultural use | M |  | unknown |  |  |  | Health departments |  | 2d; 5d

## Cat I
Category I: Water Quality Monitoring
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
I1 | Continue & expand volunteer stream monitoring program for biological markers. | M | 500 | 5000 | Program continues in place | C | C | LMWCC; Conservation Districts; MDEQ | Local funds | 1a;3b; 3f | LMWCC has VSMP records back to 2007
I2 | Continue regular phosphorus, DO and E. coli monitoring by Watershed Council. Expand this program to include all lakes in the watershed. | H | 1000 | 10000 | Program continues in place | Neew sites added as appropriate | C | LMWCC; Conservation Districts; MDEQ | LMRCC funds; local donotations; volunteer in-kind | Goal 3
I3 | Develop a database of water quality information to be maintained on publicly accessible website such as the Manistee Conservation District. | H | 1500 | 15000 | Database in place | C | C |  | local grant funds; LRBOI 2 pct. Funds; MCD funds for continuing operation | 1c; Goal 3
I4 | Continue MDEQ monitoring program to track stream biology. | H | No New Costs identified |  | MDEQ monitoring scheduled | C | C | MDEQ | Exisitng MDEQ funding | 3b | MDEQ monitoring is on a 5-year cycle
I5 | Per category H2: Actively support the portion of the Michigan Water Strategy that calls for a statewide system of groundwater and surface water monitoring. Coordinate letter of support campaign with watersheds in region. | M | No New Costs identified |  | Develop and distribute letter of support; coordinate communications | C | C | LMWCC |  | 2a;2d; 5b; 5e | This is a repeat of item H2

## CAT J
Category J: Invasive Species
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
J1 | Develop terrestrial and aquatic invasive species monitoring program for entire watershed. Create Little Manistee River task force to coordinate among the various ISN agencies. | H | Unknown |  | Task Force created | C | C | ISN groups |  | 3f; 5e | The Watershed is split among service areas of two Invasive Species Networks; This task would ensure coordination.
J2 | Use information from the monitoring program (J1) and existing strategies to develop and implement a comprehensive invasive species strategy, which will include elements of prioritization, control, education, and habitat restoration. | H |  |  | Plan in Place | C | C | Local task force; ISN groups | ISN funding | 3f;
J3 | Develop and implement plans to control or eradicate invasive phragmites on public and private sites. | M |  |  | Plan in place | C | C | ISN's; townships; property owners; USFS | Private funds | 3f
J4 | Research boat-washing methods and promote boat washing facilities throughout the watershed, in cooperation with Manistee and Benzie Conservation Districts. | H |  |  | Demonstrations of boat-washing systems twice annually in watershed. | C | C | Benzie Conservation District; Manistee County | MDNR Invasive Species pathways grant | 1a; 3d; 3f | Three mobile boat washing faciliies are available regionally
J5 | Develop educational and demonstration facilities for cleaning waders and other fishing gear at popular river entry sites | H | 500 | 3000 | Wader cleaning facility in place at Bear Track Campground | 3 stations in place | Stations in place at all popular fishing entry points | Trout Unlimited; Boy Scouts; MDNR; LMWCC | Local donations and volunteer in-kind labor. | 1a;1e; 3f

## Cat K
Category K: Wastewater and Septic Systems
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
K1 | Work with local governments to establish and enforce uniform mandatory "inspection-on-sale" regulations for septic systems throughout watershed | H | $500 per inspection | Unknown | County boards asked to consider rule | Rule inplace in Lake and Masoin counties | C | County Commissioners; Health Depts; pumping contractors; Legislature | Private inspection fees. | 1a; 1f; 3e5e | Inspection on sale regulation exists in Manistee; not other counties
K2 | Consider rules to ease the creation of community systems or other alternatives where individual septic systems are problematic | L | Unknown |  | Proposal communicated to planning commssions | C | C | Planning Commssions; Township Boards of Trustees |  | 1a; 1f; 5e
K3 | Support legislation to create statewide standards for installation, operation and inspection of on-site wastewater systems, including septic tank and drainfield systems. Coordinate with other watersheds in region. | H | No new costs identified |  | Develop streategy and letters of support; share with regional watersheds | C | C | LMWCC and regional watershed groups; Legislature | Volunteer in-kind | 1a; 3e; 5e | Michigan is only state without a statewide code
K4 | Develop educational materials to inform landowners of the proper management and impact of septic systems and fertilizers. Distribute through local health departments, volunteer groups and septic pumping companies. | M | $4,000 for materials and printing | 4000 | X | Materials developed for distribution | materials shared through townships and health departments | LMWCC. Townships, health departments; pumping contractors | local donors | 1a;3e;5e

## Cat L
Category L: Information and Education
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
L1 | Preserve the distinctive character of the Watershed by promoting rustic and natural appearance of all structures, signage and facilities at access sites. Work with campgrounds and access sites to establish voluntary uniform designs | M | Unknown |  | Establiish working group to consider designs | C | C | MDNR; USFS, Campgrounds Local governments |  | 4b; 4e;5b
L2 | Install educational kiosks or signage at appropriate sites to inform users of Watershed concerns and stewardship oppoortunities. | M | $1,000 per kiosk | 3000 | one kiosk installed | C | Three kiosks in place | MDNR; USFS, Campgrounds Local governments | Local donations; in-kind volunteer labor | 1a; 4b;4c | Include invasive species information at fishing access sites
L3 | Develop a list of all riparian property owners for dissemination of edicational and informational materials. | H |  | 2000 | List in place | List Updated semi-annually | C | County governments | In Kind volunteer labor | 1b
L4 | Assign communications element (group or individual) within LMWCC to promote Watershed education through multiple pathways, including in-school programs, local media, public presentations and direct mail. | M |  | Unknown | Commiunication group and strategy inentified | C | C | LMWCC; Schoools, Libraries |  | 1a; 5e
L5 | Establish a program of outreach to developers and real estate professionals to share research showing that clean water and land stewardship can positively impact property values, and to communicate the range of possible land protection strategies. | M |  | Unknown | Contact list established; Outreach in place | C | C | LMWCC communication group; local Realtors |  | 1a; 1f
L6 | Maintain updated versions of the WMP on a publicly accessible website, and provide hard copies to libraries in and near the Watershed. | H |  | Unknown | Plans available | C | C | LMWCC; Schoools, Libraries |  | 1a; 1b
L7 | Create grant-supported project to inform/educate township governments and the public of the role of land use BMP's in maintaning water quality. | H | 25000 | 25000 | Project Planning | Funding secured; project begins | C | LMWCC | Foundation grants; LRBOI |  | This funding is also accounted for in task C1