## Cat A
Category A: Shoreline/Streambank Issues
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
A1 | Restore severe and moderate streambank erosion sites identified in CRA inventory. Use whole-tree revetments where practicable to improve aquatic habitat while stabilizing streambanks. | H | $120 per linear foot | 300000 | 5 sites restored | C | 10 additional sites restored | LMWCC, CRA | Private property owners; Fisheries Trust; Grants | 2; 3c; 3e | Sites included by reference from inventory at www.northernmichiganstreams.com
A2 | Update streambank inventory on Little Manistee River and major tributaries on 10-year cycle. | M |  | 18000 | X | Inventory updated | X | CRA | Trout Unlimited; G.L. Fisheries Trust | 3c; 3e | Could be expanded to include streamside habitat (F5) and invasive species (F6) inventories.
A3 | Work with conservation districts and MSU extension to demonstrate natural shoreline protection techniques on Cool, Harper and other developed lakes in the Watershed. | M | $5,000 per site | 15000 | One site demonstration complete | C | C | Lake Associations; property owners | Private Property owners; MSUE; Cons. Dists | 3c | Work through Michigan Natural Shoreline Partnership and local certified contractors
A4 | Complete removal of sand-berm dam at Syers Lake to restore natural lake configuration and perenneal flow to Syers Creek | H | 120000 | 120000 | Project complete | Creek monitored | C | CRA; LMWCC; private landowners | LMWCC; T.U.; Grants; Private landowner funds | 2e | Funding committed for 2018/2019
A5
A6

## Cat B
Category B: Stormwater and Run-off
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
B1 | Update stormwater infrastructure and impervious surface maps. Identify problem sites and institute Green Infrastructure BMP's for all new construction. | L | unknown |  | X | Maps and BMP education in place | C | County Planning Departments; MSUE; Networks Northwest | Local foundations; in-kind funding | 2d; 3c
B2 | Inventory & monitor all streams for nutrients, E. coli, and other pollutants, including thermal stressors. Institute BMP's as appropriate. | H | See task I2 | See task I2 | Existing program continues | Progbram expanded to additional sites | C | LMWCC | LMWCC funds; volunteers | 3a; 3b; 3e | This is a continuation and expansion of existing LMWCC program. For costs, see I2
B3 | Promote shoreline stewardship education through Michigan Natural Shoreline Partnership and local conservation districts | M | no new costs identified |  | X | Information available on Websites or through Township mailings | C | Conservation Districts; MNSP; |  | 3c; 3e
B4 | Promote reforestation of public and private lands within the stream corridor to reduce storm runoff and thermal pollution. | H | $5,000 per year | 50000 | Sites identified | Reforestation activity on 5 sites | Reforestation activity on 10 sites | Conservation districts; Private land owners; U.S. Forest Service; MDNR | Private funds; grants | 2a; 2c; 2d | This task is important due to loss of ash, oak and beech trees to insects and disease.
B5 | Encourage voluntary private land stewardship practices such as native plantings, rain gardens, conservation easements, and preservation of wildlife habitat. | H | $2,000 per rain garden | 24000 | 2 rain gardens installed | 5 rain gardens installed | 12 (total) rain gardens installed | Private funds | MSUE; Conservation districts | Goal 2; 3a

## Cat C
Category C: Planning, Zoning and Land Use
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
C1 | Work with township and county planners to develop cooperative land-use practices that extend across government boundaries to protect the entire watershed. | H | $5,000 per township | 80000 | Create multi-jurisductional task force | Funding secured | Program in place | Townships; MSUE; LMWCC; AES | Will require outside grant asistance. Tribal 2 pct. Funding | Goal 1; Goal 5 | See task L7. This task must be coordinated with I/E component
C2 | Identify locally important viewsheds, incorporate protection into master plans and local zoning ordinances to maintain the natural and rustic character of the watershed. | M | Included in C1 |  | X | Sites identified for protection | C | LMWCC; Audubon Clubs; | N/A | Goal 4 | Maintaining rustic, natural character was an objective of both the 2000 WMP and the present document
C3 | Develop and adopt ordinances to prevent introduction of terrestrial and aquatic invasive species, and permit treatment of existing infestations | M | No new costs identified |  | Provide model ordinances to townships | C | C | MTA; ISN; township govts | N/A | 1d; 3f | Model ordinances available through ISN's. May require state legislation
C4 | Investigate the possibility of a multi-jurisdictional zoning ordinance or overlay district to establish uniform, locally based rules for development within the Little Manistee Watershed and River Corridor. Work with township governments to establish such protections when public support exists. | H | See C1 |  | See C1 | C | C | Townships; MSUE; LMWCC; AES | N/A | Goal 1; Goal 5 | This is a specific task included in the more general actiivities of C1
C5 | Promote 'green infrastructure' principles including cluster development for rural residential, and low impact stormwater design requirements as part of local planning and zoning process for new developments. | L | No costs identified |  | See C1 | C | C | Townships; MSUE; LMWCC; AES | N/A | 5a | This is a specific task included in the more general actiivities of C1
C6 | Begin public education regarding the pros and cons of Michigan Natural River designation; promote such designation if local support exists. | H | Variable |  | X | River forums conducted | C | LMWCC; MDNR; TU. | N/A | 1f | This requires coordination with I/E program as well as local planners. Natural river designation is not under consideration at this time.
C7 | Seek grant funding and fiduciary partners to hire or contract with a person for work on implementation of the WMP | H | $25,000 annually | 250000 | Implementation staff person in place | C | C | LMWCC, Conservation Districts; CRA | Tribal Grants, Local foundations | All Goals | Employee may be full- or part-time. If no funding is received, LMWCC volunters will continue to lead implementation.

## Cat D
Category D: Road-Stream Issues
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
D1 | Update existing stream crossing inventory every 10 years to reflect changes & document improvements | H | 15000 | 15000 | X | New Inventory Complete | C | CRA; LMWCC | Tribal 2 pct. Funding; Great Lakes Fisheries Trust | 2e; 3e | Current inventory completed in 2014
D2 | Restore and protect 74 road-stream crossings identified in the inventory as sites of severe or moderate concern, using appropriate BMP's. Restore and protect additional sites on road-stream crossing inventory as conditions require and funding becomes available. | H | varies | 4280000 | 5 sites addressed | 15 sites addressed | All severe and moderate sites improved | CRA; LMWCC; MDoT; road commissions | Grant funding required; Road commissions; MDOT; MDEQ | 2e; 3e | Cost cited is for 74 sites, per 2014 inventory. Estimates may change as new needs are identified
D3 | Identify sites where private roads may have an impact on surface water qualiity. Work with property owners to minimize movement of sediments, nutrients, salts, etc. into adjacent water | M | varies |  | X | Sites Identified | C | Private land owners; CRA | Private funds | 3e
D4 | Develop & institute policies regarding use of dust control agents on unpaved roads near surface waters. Institute BMPs to prevent dust-control agents from entering surface waters. | L | unknown |  | X | Policies developed | C | Road Commissions; MDOT; MDEQ | N/A | 3e

## Cat E
Category E: Land Protection and Management
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
E1 | Work with Land Conservancies and/or other agencies to develop a systematic priority parcel analysis for significant lands in Mason County and Lake County segments of the Watershed. Update the existing analysis for the Manistee County segment. | M |  | 10000 | Manistee analysis cmplete | Analysis complete for Lake and Mason | C | GTRLC; Land Conservancies | Grants; private donations | 4b; 4f; Goal 5
E2 | Assist and support USFS, MDNR and/or local government acquisition of property for protection of water quality, threatened or endangered species, wildlife habitat and other sensitive ecological features | M |  | 500000 | X | 2 sites protected | C | MDNR; USFS; townships; Land conservancies | Nat. Res. Trust Fund. USFS funds | Goal 5 | Acquisition from willing sellers only.
E3 | Support land-protection and land purchase activities on high-priority sites throughout watershed, including conservation easements and transfer/purchase of development rights where appropriate. | H |  | 500000 | X | 2 sites protected | C | Land Conservancies; private land owners | Nat. Res. Trust Funds; Private donations | Goal 5 | Conservation Easements are generally favored, since the watershed already has significant acreage in public ownership
E4 | Promote participation in NRCS programs and Michigan Agriculture Environmental Assurance Program (MAEAP) to encourage BMP's in agricultural operations | L |  | No costs identified | X | 1 farm certified | C | Farm owners; MDARD | N/A | 3e
E5 | Use expertise of MSU Extension and Osceola-Lake Conservation District to educate farmers and riparian residents on use of buffer strips and cover crops to improve soil and manage storm runoff. | M |  | Unknown | Education programs offered and publicized | C | C | MSUE; Conservation Districts; land owners | N/A | Goal 1; 2a; 3c; 3e

## Cat F
Category F: Habitat for Fish and Wildlife
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
F1 | Maintain multiple-use management policies on public lands. Preserve upland habitat and wildlife corridors. Discourage new roads in state forest and wetland areas | H |  | No new costs | Continuation of current practice | C | C | USFS; MDNR | N/A | 4a; 4b; 4c | This is a continuation of current policies
F2 | Conduct fishery surveys on the Little Manistee River on a minimum 10 year cycle to monitor changes & evaluate stocking & managment programs. | H |  | 30000 | X | New survey complete | C | MDNR; Trout unlimited; LRBOI | MDNR funds | 4a; 4e
F3 | Maintain current fish stocking & management strategies unless changes are warranted by scientific studies such as in F2 | M |  | No New costs | C | C | C | MDNR; Trout unlimited; LRBOI | N/A | 4a | Continuation of current policies
F4 | Install and maintain fish habitat improvement structures as appropriate. Consider instream habitat and fish passage implications of all road crossing and bank stabilization projects. | M | $10,000 per site | 120000 | Woody debris installed, per plan | C | C | LMWCC; MDNR; CRA; Trout unlimited | Private donations; volunteer in-kind | Goal 2 | Funds committed for woody debris work in 2018/2019
F5 | Evaluate & document stream and streamside habitat, including shade and forest cover for the Little Manistee River and major tributaries. | M |  | Not identified (See A2) | X | Evaluation complete | X | USFS; MDNR; LMWCC | N/A | Goal 2 | This can be included in an enhanced bank erosion survey (A2)
F6 | Restudy & document habitat and fishery potential in each of small lakes and streams in watershed, many of which have not been evaluated in more than 50 yrs. | L |  | 50000 | X | Inventory complete | X | MDNR; private land owners | Grants; MDNR funds; lake associations | 4a
F7 | Evaluate fishery potential in the Luther Millpond and sites upstream of the Luther Dam. | H | 30000 | 30000 | Develop plans for cooperative study with MDNR; Village and Township | Complete Study | Publicize study's results and recommendation | Ellsworth Twp.; Village of Luther; Trout Unlimited; MDNR; LMWCC | Grants; LRBOI; TU; MDNR | 1a; 1f
F8 | Closely monitor operation of Luther Dam and spillway. Recommend changes as appropriate. Specify which agency (Village or MDNR) is responsible for operation of the dam. | H | No new costs identified |  | Develop operation and monitoring plan | C | C | Village of Luther; Ellsworth Twp. MDNR; LMWCC | Village and township funds | 2b; 2e | This item could be a short-term option or a long-term option, depending on action in F9
F9 | Develop long-term options for removal of the Luther Dam and restoration of the Millpond and park area and upstream tributaries. Recognize that the dam is the property of the village, and removal/restoration can occur only if village residents and officials determine it is in their best interests. | M |  | Variable: $50,000 to $2 million | Phase 1; create working group; identify long term costs and benefits of maintaining the dam/millpond | Phase 2: identify benefits and costs of fish passage, stream restoration; dam removal or operational changes | Phase 3: Act on appropriate phase 2 findings | Village of Luther; Ellsworth Twp. LMWCC; MDNR; MDEQ | State or federal grants required | 1a; 2b; 2e | Changes in dam operation and/or fish passage may have modest costs; Dam removal and stream restoration would cost up to $2 million

## Cat G
Category G: Recreation, Safety, Navigation and Human Health
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
G1 | Continue and expand volunteer monitoring for E. coli and other pothential pathogens | H | See task I2 | See task I2 | Monitoring in place | C | C | LMWCC; lake associations |  | 3a; 3b | E. coli monitoring costs are incuded with general monitoring in task I2
G2 | Work with State Forest and National Forest staff and ORV groups to ensure that motorized trails are designed and used in ways that do not negatively impact water quality. | H | No new costs identified |  | Trails inspected and site issues identifieid | Sites corrected | C | MDNR; USFS; Snowmobile and ORV organizations | Trail program funds | 4b; 4c; 4e
G3 | Initiate "adopt a stream" or similar volunteer program for ongoing river clean-up and tree management. | M | No new costs identified |  | Program in place | C | C | Conservation Districts; | N/A | 1c; 1e
G4 | Monitor paddlecraft volume to ensure that such use does not exceed the river's carrying capacity. | L | No new costs identified |  | Monitoring dates/criteria identified | Program in place | C | LMRCC; Private Landowners |  | 4b; 4d; 4e
G5 | Keep at least one campground open through October to accommodate late-season padlers | M | Unknown |  | Campground operational costs and options assessed | C | C | Campground operators | N/A | 4b; 4d | Proposed by the public at informational session

## Cat H
Category H: Hydrology, Groundwater and Wetlands
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
H1 | Install and monitor permanent gauges throughout watershed to evaluate & report stream flow, water temperature, and high-low water conditions. Investigate emerging technologies for automatic sensors, if USGS gauging is not available. | H | variable | $10,000 - $35,000 | Permanent gauges in place | C | C | LMWCC; Conservation Districts; USFS; USGS; MDNR | USGS; Local donors | 2a | $35,000 is estimate for USGS gauging station
H2 | Study and Implement a system of local groundwater monitoring to assess both flow levels and quality of this vital resource. Actively support legislation to develop a statewide system of groundwater and surface water monitoring. | H | variable | 50000 | Collect aquifer data and design monitoring strategy | Monitoring begins | C | LMWCC; District Health Departments; Michigan Legislature | N/A | 2a; 2d; 5c; 5e | Costs may vary widely depending on study design. Funding for statewide program is preferred.
H3 | Work with local government to regulate installation of new impervious surfaces in the stream corridor and mandate BMP's to control stormwater and mitigate impact of new and existing impervious surfaces. | M |  | No new costs | X | Impervious surface policies in effect | C | Twp planning comms. | Grants, in-kind labor | 1a; 1f; 2d; 3c; 4e | This element of groundwater protection is also included in categories B and C, and in education component (Cat L)
H4 | Protect wetland areas from development; initiate programs to educate the public about the role of wetlands in water quality | M |  | 5000 | X | Wetland program offered to schools and service groups | C | MDEQ; MDNR, Twp. Planning comms.; LMWCC | Conservation Districts; Inland Lake Groups; townships | 1a;2a; 2d | Wetland education costs also included in I/E progam estimates (Category L)
H5 | Adopt state and local rules, protective of groundwater, to monitor and regulate the practices of horizontal drilling & hydraulic fracturing for oil & gas extraction, including associated infrastructure and disposal facilities | H |  | unknown | C | C | C | Legislature, MDEQ, Twp planning comms. | N/A | 2a; 2d; 4f
H6 | Monitor for nitrates in well water, especially at sites with light soils and historic agricultural use | M |  | unknown | C | C | C | Health departments | N/A | 2d; 5d

## Cat I
Category I: Water Quality Monitoring
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
I1 | Continue & expand volunteer stream monitoring program for biological markers. | M | 500 | 5000 | Program continues in place | C | C | LMWCC; Conservation Districts; MDEQ | Local funds | 1a;3b; 3f | LMWCC has VSMP records back to 2007
I2 | Continue regular phosphorus, DO and E. coli monitoring by Watershed Council. Expand this program to include all lakes in the watershed. Add monitoring of thermal conditions | H | 5000 | 50000 | Program continues in place | Neew sites added as appropriate | C | LMWCC; Conservation Districts; MDEQ | LMRCC funds; local donotations; volunteer in-kind | Goal 3 | This funding includes monitoring in tasks B2 and G1
I3 | Develop a database of water quality information to be maintained on publicly accessible website such as the Manistee Conservation District. | H | 1500 | 15000 | Database in place | C | C | LMWCC; Conservation Districts | local grant funds; LRBOI 2 pct. Funds; MCD funds for continuing operation | 1c; Goal 3
I4 | Continue MDEQ monitoring program to track stream biology. | H | No New Costs identified |  | MDEQ monitoring scheduled | C | C | MDEQ | Exisitng MDEQ funding | 3b | MDEQ monitoring scheduled for 2019 on a 5-year cycle
I5 | Per category H2: Actively support the portion of the Michigan Water Strategy that calls for a statewide system of groundwater and surface water monitoring. Coordinate letter of support campaign with watersheds in region. | M | No New Costs identified |  | Develop and distribute letter of support; coordinate communications | C | C | LMWCC | N/A | 2a;2d; 5b; 5e | This expands on a portion of item H2

## CAT J
Category J: Invasive Species
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
J1 | Develop terrestrial and aquatic invasive species monitoring program for entire watershed. Create Little Manistee River task force to coordinate among the various ISN agencies. | H |  | Unknown | Task Force created | C | C | ISN groups | N/A | 3f; 5e | The Watershed is split among service areas of two Invasive Species Networks; This task would ensure coordination through periodic meetings.
J2 | Use information from the monitoring program (J1) and existing strategies to develop and implement a comprehensive invasive species strategy, which will include elements of prioritization, control, education, and habitat restoration. | H |  | 20000 | Plan in Place | C | C | Local task force; ISN groups | ISN funding; local volunteers | 3f;
J3 | Develop and implement plans to control or eradicate invasive phragmites on public and private sites. | M | 1000 | 10000 | Plan in place | C | C | ISN's; townships; property owners; USFS | Private funds | 3f
J4 | Research boat-washing methods and promote boat washing throughout the watershed, in cooperation with Manistee County and the Benzie Conservation District. | H | No new costs identified |  | Demonstrations of boat-washing systems twice annually in watershed. | C | C | Benzie Conservation District; Manistee County | MDNR Invasive Species pathways grant | 1a; 3d; 3f | Three mobile boat washing faciliies are available regionally
J5 | Develop educational and demonstration facilities for cleaning waders and other fishing gear at popular river entry sites | H | 2000 | 20000 | Wader cleaning facility in place at Bear Track Campground | 3 stations in place | Stations in place at all popular fishing entry points | Trout Unlimited; Boy Scouts; MDNR; LMWCC | Local donations and volunteer in-kind labor. | 1a;1e; 3f | May be co-located with kiosks in task L2
J6 | Float navigable segments of mainstream with Invasive Species Network staff to inventory terrestrial and emergent invasives | M |  | 15000 | X | Inventory complete | C | LMWCC, ISN's | LRBOI grant; in-kind labor | 1a, 3f | Could be combined with streambank inventory (A2) for cost savings

## Cat K
Category K: Wastewater and Septic Systems
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
K1 | Work with local governments to establish and enforce uniform mandatory "inspection-on-sale" regulations for septic systems throughout watershed | H | $300 per inspection | 330000 | County boards asked to consider rule | Rule inplace in Lake and Masoin counties | C | County Commissioners; Health Depts; pumping contractors; Legislature | Private inspection fees. | 1a; 1f; 3e5e | State legislation (See K3) is preferable. Cost estimate based on inspection of 25 percent of systems during 10 year period.
K2 | Consider rules to ease the creation of community systems or other alternatives where individual septic systems are problematic | L |  | Unknown | Proposal communicated to planning commssions | C | C | Planning Commssions; Township Boards of Trustees | N/A | 1a; 1f; 5e
K3 | Support legislation to create statewide standards for installation, operation and inspection of on-site wastewater systems, including septic tank and drainfield systems. Coordinate with other watersheds in region. | H | Unknown | Unknown | Develop streategy and letters of support; share with regional watersheds | C | C | LMWCC and regional watershed groups; Legislature | N/A | 1a; 3e; 5e | Michigan is only state without a statewide code. Costs would likely be borne by property owners, as in K1
K4 | Develop educational materials to inform landowners of the proper management and impact of septic systems and fertilizers. Distribute through local health departments, volunteer groups and septic pumping companies. | M | $5,000 for materials and printing | 5000 | X | Materials developed for distribution | materials shared through townships and health departments | LMWCC. Townships, health departments; pumping contractors | local donors | 1a;3e;5e

## Cat L
Category L: Information and Education
Task |  | Priority | Unit Cost | Estimated Total Cost | Milestone 2018-21 | Milestone 2022-25 | Milestone 2026-28 | Potential Project Partners | Potential Funding Sources | Objectives Addressed | Notes
L1 | Preserve the distinctive character of the Watershed by promoting rustic and natural appearance of all structures, signage and facilities at access sites. Work with campgrounds and access sites to establish voluntary uniform designs | M | Unknown |  | Establiish working group to consider designs | C | C | MDNR; USFS, Campgrounds Local governments |  | 4b; 4e;5b
L2 | Install educational kiosks or signage at appropriate sites to inform users of Watershed concerns and stewardship opportunities. | M | $1,000 per kiosk | 3000 | one kiosk installed | C | Three kiosks in place | MDNR; USFS, Campgrounds Local governments | Local donations; in-kind volunteer labor | 1a; 4b;4c | May include invasive species information and wader-cleaning station at fishing access sites
L3 | Develop a list of all riparian property owners for dissemination of edicational and informational materials. | H |  | 2000 | List in place | List Updated semi-annually | C | County governments | In-kind volunteer labor | 1b
L4 | Assign communications element (group or individual) within LMWCC to promote Watershed education through multiple pathways, including in-school programs, local media, public presentations and direct mail. | M | $3,000 per year | 30000 | Commiunication group and strategy inentified | C | C | LMWCC; Schools; Libraries | Local foundations; LRBOI | 1a; 5e
L5 | Establish a program of outreach to developers and real estate professionals to share research showing that clean water and land stewardship can positively impact property values, and to communicate the range of possible land protection strategies. | M |  | 5000 | Contact list established; Outreach in place | C | C | LMWCC communication group; local Realtors | Local funds | 1a; 1f
L6 | Maintain updated versions of the WMP on a publicly accessible website, and provide hard copies to libraries in and near the Watershed. | H |  | 1000 | Plans available | C | C | LMWCC; Schools, Libraries |  | 1a; 1b | Ideally, water quality database will be on same website
L7 | Create grant-supported project to inform/educate township governments and the public of the role of land use BMP's in maintaning water quality. | H | 40000 | 40000 | Project Planning | Funding secured; project begins | C | LMWCC | Foundation grants; LRBOI |  | This task creates additional funding to extend the work in task C1
L8 | Include review of WMP implementation progress as an agenda itemfor annual membership meeting of LMWCC | M | No new costs | No new costs | Annual review in place | C | C | LMWCC; all partners invited to participate | None Needed | All Goals | Annual review will incude progress reports and opportunity to amend the plan
L9 | Conduct an annual day long meeting of all interested stakeholders to review the status of the plan, update it and and set Goals and Objectives for the upcoming year(s). | H | No New Costs |  | Initial meeting scheduled for Feb.2 2018. | Annual Meetings | Annual Meetings | All interested Stakeholders | None Needed | All Goals | Annual review will incude progress reports and opportunity to amend the plan